|  | STATUS REPORT |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ChicoWeb | WEEK 4 |  |  |  | # Period: 22/12 – 28/12 |  |  | SR-241-01-SS |  |
| Schedule | Planned start: 01/12 |  |  |  | Actual start: 01/12 |  |  |  |  |
|  | Planned end: 30/12 |  |  |  | Actual end: -- |  |  |  |  |
| Budget | Planned budget: $ 13.320,00 |  |  |  | Actual total cost: $ 12.940,00 |  |  |  |  |
| Plan week 4 | ID | Activity |  | Planned cost |  | Planned progress | Planned start |  | Planned end |
|  | 1.4 | Monitor & control week 4 |  | $ 2.000,00 |  | 100% | 22/12 |  | 26/12 |
|  | 2.4.1 | Plan system tests |  | $ 160,00 |  | 100% | 22/12 |  | 22/12 |
|  | 2.4.2 | Execute system tests |  | $ 160,00 |  | 100% | 23/12 |  | 23/12 |
|  | 2.5.1 | Install system |  | $ 160,00 |  | 100% | 24/12 |  | 24/12 |
|  | 2.5.2 | Verify and accept project |  | $ 160,00 |  | 100% | 25/12 |  | 25/12 |
|  | 3.1 | Prepare training material |  | $ 240,00 |  | 100% | 25/12 |  | 25/12 |
|  | 3.2 | Realize training |  | $ 240,00 |  | 100% | 26/12 |  | 26/12 |
| Activities realized during week 2 |  |  |  |  |  |  |  |  |  |

| ID | Activity | Responsible | Effort spent (person-hours) | Actual cost | Actual start | Actual end | Completed |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.4 | Monitor & control week 4 | Leonardo | 10 | $ 500,00 | 22/12 | 26/12 | 25% |
| 2.4.1 | Plan system tests | Karen | 8 | $ 160,00 | 22/12 | --- | 50% |
|  |  | Mauricio | 4 | $ 240,00 |  |  |  |
| 2.4.2 | Execute system tests | Karen | 8 | $ 160,00 | 23/12 | --- | 50% |
| 2.5.1 | Install system | Karen | 2 | $ 40,00 | 24/12 | --- | 0% |
| 2.5.2 | Verify and accept project | Karen | 0 | --- | --- | --- | 0% |
| 3.1 | Prepare training material | João | 0 | --- | 25/12 | --- | 50% |
|  |  | Maurício | 4 | $ 240,00 |  |  |  |
| 3.2 | Realize training | João | 0 | --- | --- | --- | 0% |

## Earned Value Management

| Week | Planned value | Actual cost | Earned Value | SV | CV | SPI | CPI |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Week 1 | $ 3.600,00 | $ 3.280,00 | $ 3.280,00 | $ -320,00 | $ 0,00 | 0,91 | 1,0 |
| Week 2 | $ 6.600,00 | $ 6.600,00 | $ 6.600,00 | $ 0,00 | $ 0,00 | 1,0 | 1,0 |
| Week 3 | $ 10.200,00 | $ 11.600,00 |  |  |  |  |  |
| Week 4 |  |  |  |  |  |  |  |

## Issues:

- All employees who worked on 25/12 are receiving overtime payment​​.

- The intern Karen was quite lost on running tests. She did not even know how to begin. Therefore, Mauricio helped here on the night of 22/12 to plan at least some tests.

- When Karen arrived at the pizzeria on December, 24 to install the system, the pizzeria was closed due to Christmas vacations.

- Leonardo tried to locate the owner of the pizzeria to solve the problem, but the owner was away on vacation.

- On December, 25/26, John simply did not appear for work. Calling Mauríco, he agreed to come and prepared the training.

- The Christmas party was a great success - everyone stayed until late.

Leonardo

Leonardo – Project manager