|  | STATUS REPORT |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ChicoWeb | WEEK 1 |  |  |  |  | # Period: 01/12 – 07/12 |  |  | SR-241-01-SS |  |
| Schedule | Planned start: 01/12 |  |  |  |  | Actual start: 01/12 |  |  |  |  |
|  | Planned end: 30/12 |  |  |  |  | Actual end: -- |  |  |  |  |
| Budget | Planned budget: $ 13.320,00 |  |  |  |  | Actual total cost: $ 3.280,00 |  |  |  |  |
| Plan week 1 | ID | Activity |  |  | Planned cost |  | Planned progress | Planned start |  | Planned end |
|  | 1.1 |  | Monitor & control week 1 |  | $ 2000,00 |  | 100% | 01/12 |  | 30/12 |
|  | 2.1.1 |  | Elicit requirements |  | $ 240,00 |  | 100% | 01/12 |  | 01/12 |
|  | 2.1.2 |  | Analyze requirements |  | $ 240,00 |  | 100% | 02/12 |  | 02/12 |
|  | 2.1.3 |  | Review requirements |  | $ 240,00 |  | 100% | 03/12 |  | 03/12 |
|  | 2.2.1 |  | Design system architecture |  | $ 240,00 |  | 100% | 04/12 |  | 04/12 |
|  | 2.2.2 |  | Design database |  | $ 400,00 |  | 100% | 04/12 |  | 05/12 |
|  | 2.2.3 |  | Design interface |  | $ 240,00 |  | 100% | 05/12 |  | 05/12 |
| Activities realized during week 1 |  |  |  |  |  |  |  |  |  |  |

| ID | Activity | Responsible | Effort spent (person-hours) | Actual cost | Actual start | Actual end | Completed |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Monitor & control week 1 | Leonardo | 40 | R$ 2000,00 | 01/12 | 30/12 | 100% |
| 2.1.1 | Elicit requirements | João | 8 | R$ 240,00 | 01/12 | 01/12 | 100% |
| 2.1.2 | Analyze requirements | João | 8 | R$ 240,00 | 02/12 | 02/12 | 100% |
| 2.1.3 | Review requirements | João | 8 | R$ 240,00 | 03/12 | 03/12 | 100% |
| 2.2.1 | Design system architecture | Mauricio | 8 | R$ 240,00 | 04/12 | 04/12 | 100% |
| 2.2.2 | Design database | Vitor | 8 | R$ 200,00 | 04/12 | --- | 50% |
| 2.2.3 | Design interface | Mauricio | 4 | R$ 120,00 | 05/12 | --- | 50% |

## Earned Value Management

| Week | Planned value | Actual cost | Earned Value | SV | CV | SPI | CPI |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Week 1 | $ 3.600,00 | $ 3.280,00 | $ 3.280,00 | $ -320,00 | $ 0,00 | 0,91 | 1,0 |

## Issues:

- SoftSolution received a request for a new major project. Vitor and Mauricio helped in preparing the proposal this week.

- The coffee machine is broken and needs to be replaced urgently.

Leonardo

Leonardo – Project manager