# ANSWER SHEET

Group/Names:

Completing the earned value management calculations:

| Week | Planned value |  | Actual cost | Earned Value | SV | CV | SPI | CPI |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Week 3 |  | $ 10.200,00 | $ 11.600,00 | $ 10.200,00 | $ 0,00 | $ -1.400,00 | 1,0 | 0,88 |
| Week 4 |  | $ 13.320,00 | $ 12.940,00 | $ 10.980,00 | $ -2.340,00 | $ -1.960,00 | 0,82 | 0,85 |

Issues identified:

|  | Late? (Yes/No) | Spending more than the planned cost for the quantity of work done? (Yes/No) | Cause |
| --- | --- | --- | --- |
| Week 1 | S | N | Vitor and Maurício have worked less than planned because they helped to write a proposal for another project. |
| Week 2 | N | N | -- |
| Week 3 | N | S | Spending more than the planned cost due to overtime, as Alberto has also worked on the implementation of the administrative module. |
| Week 4 | S | S | Due to diverse overtimes and absences during the holidays and Karen’s lack of competence regarding tests. |