|  | STATUS REPORT |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ChicoWeb | WEEK 3 |  |  |  | # Period: 15/12 – 21/12 |  |  | SR-241-01-SS |  |
| Schedule | Planned start: 01/12 |  |  |  | Actual start: 01/12 |  |  |  |  |
|  | Planned end: 30/12 |  |  |  | Actual end: -- |  |  |  |  |
| Budget | Planned budget: $ 13.320,00 |  |  |  | Actual total cost: $ 11.600,00 |  |  |  |  |
| Plan week 3 | ID | Activity |  | Planned cost |  | Planned progress | Planned start |  | Planned end |
|  | 1.3 | Monitor & control week 3 |  | $ 2.000,00 |  | 100% | 15/12 |  | 19/12 |
|  | 2.3.2 | Implement order module |  | $ 1.000,00 |  | 100% | 15/12 |  | 19/12 |
|  | 2.3.3 | Implement administrative module |  | $ 600,00 |  | 100% | 15/12 |  | 17/12 |
| Activities realized during week 2 |  |  |  |  |  |  |  |  |  |

| ID | Activity | Responsible | Effort spent (person-hours) |  | Actual cost | Actual start | Actual end | Completed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.3 | Monitor & control week 3 | Leonardo | 40 | $ 2.000,00 |  | 15/12 | 19/12 | 100% |
| 2.3.2 | Implement order module | Alberto | 40 | $ 1.000,00 |  | 15/12 | 19/12 | 100% |
| 2.3.3 | Implement administrative module | Alberto | 40 | $ 2.000,00 |  | 16/12 | 21/12 | 100% |

## Earned Value Management

| Week | Planned value | Actual cost | Earned Value | SV | CV | SPI | CPI |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Week 1 | $ 3.600,00 | $ 3.280,00 | $ 3.280,00 | $ -320,00 | $ 0,00 | 0,91 | 1,0 |
| Week 2 | $ 6.600,00 | $ 6.600,00 | $ 6.600,00 | $ 0,00 | $ 0,00 | 1,0 | 1,0 |
| Week 3 | $ 10.200,00 | $ 11.600,00 |  |  |  |  |  |

## Issues:

- Leonardo tried to solve problems and did not have time to calculate the earned value management indicators. ​​

- Paulo suffered a motorcycle accident over the weekend and is hospitalized at the Regional Hospital. Probably, he will be back to work only in March next year.

- Alberto also implemented the administrative module during the evenings/nights and on Saturday.

- Sleeping on the couch at the entrance of the company, Alberto is requesting the purchase of a more comfortable sofa.

Leonardo

Leonardo – Project manager