|  | STATUS REPORT |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ChicoWeb | WEEK 2 |  |  |  | # Period: 08/12 – 14/12 |  |  | SR-241-01-SS |  |
| Schedule | Planned start: 01/12 |  |  |  | Actual start: 01/12 |  |  |  |  |
|  | Planned end: 30/12 |  |  |  | Actual end: -- |  |  |  |  |
| Budget | Planned budget: $ 13.320,00 |  |  |  | Actual total cost: $ 6.600,00 |  |  |  |  |
| Plan week 2 | ID | Activity |  | Planned cost |  | Planned progress | Planned start |  | Planned end |
|  | 1.2 | Monitor & control week 2 |  | $ 2.000,00 |  | 100% | 08/12 |  | 12/12 |
|  | 2.3.1 | Implement menu module |  | $ 2000,00 |  | 100% | 08/12 |  | 12/12 |
| Activities realized during week 2 |  |  |  |  |  |  |  |  |  |

| ID | Activity | Responsible | Effort spent (person-hours) | Actual cost | Actual start | Actual end | Completed |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.2 | Monitor & control week 2 | Leonardo | 40 | $ 2.000,00 | 08/12 | 12/12 | 100% |
| 2.2.2 | Design database | Vitor | 8 | $ 200,00 | 08/12 | 08/12 | 100% |
| 2.2.3 | Design interface | Mauricio | 4 | $ 120,00 | 08/12 | 08/12 | 100% |
| 2.3.1 | Implement menu module | Lucas | 40 | $ 1000,00 | 08/12 | 12/12 | 100% |

## Earned Value Management

| Week | Planned value | Actual cost | Earned Value | SV | CV | SPI | CPI |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Week 1 | $ 3.600,00 | $ 3.280,00 | $ 3.280,00 | $ -320,00 | $ 0,00 | 0,91 | 1,0 |
| Week 2 | $ 6.600,00 | $ 6.600,00 | $ 6.600,00 | $ 0,00 | $ 0,00 | 1,0 | 1,0 |

## Issues:

- It has been decided that company’s Christmas party will be held on December, 22. There will be held a "secret friend gift exchange" in which participants should buy gifts with a value of $ 10.00.

- Paulo alerted for buying different snacks than last year, as he suffered from food poisoning from the food served at last year’s Christmas party and had to stay 20 days at the hospital.

Leonardo

Leonardo – Project manager