Calculating the earned value indicators 
         for week 2 ...

| ID | Activity | Planned cost | Completed | Calculating |
| --- | --- | --- | --- | --- |
| 1.1 | Monitor & control week 1 | $ 2.000,00 | 100% | $ 2.000 (Planned cost * % completed) |
| 1.2 | Monitor & control week 2 | $ 2.000,00 | 100% | $ 2.000 |
| 2.1.1 | Elicit requirements | $ 240,00 | 100% | $ 240 |
| 2.1.2 | Analyze requirements | $ 240,00 | 100% | $ 240 |
| 2.1.3 | Review requirements | $ 240,00 | 100% | $ 240 |
| 2.2.1 | Design system architecture | $ 240,00 | 100% | $ 240 |
| 2.2.2 | Design database | $ 400,00 | 100% | $ 400 |
| 2.2.3 | Design interface | $ 240 | 100% | $ 240 |
| 2.3.1 | Implement menu module | $ 1.000,00 | 100% | $ 1.000 |
| Earned Value (summing up ) |  |  |  | R$ 6.600 |

Earned Value Management (using cumulative values)

PV – Planned Value is the authorized budget assigned to the work to be accomplished for an activity.

AC – Actual Cost is the total cost actually incurred and recorded in accomplishing work performed for an activity.

EV – Earned Value is the value of work performed expressed in terms of the

approved budget assigned to that work for an activity.

.

Schedule Variance (SV) is a measure of schedule performance calculated by: 
SV = EV – PV.

Cost Variance (CV) is a measure of cost performance calculated by: 
CV = EV – AC.

Schedule Performance Index (SPI) is a measure of progress achieved compared to progress planned on a project. SPI = EV / PV

Cost Performance Index (CPI) is a measure of the value of work completed compared to the actual cost or progress made on the project. CPI = EV / AC

.

: